## PRODUCT BACKLOG
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | User Story Point | Assignee | Status
1 | 1 | 1 | Front end home page | MUST HAVE | 3 | smriti | 3- Completed
|  | 2 | Front end user login page | MUST HAVE | 3 | smriti | 3- Completed
|  | 3 | Front end user contact page | MUST HAVE | 3 | smriti | 3- Completed
|  | 4 | Front end user about page | MUST HAVE | 3 | smriti | 3- Completed
|  | 5 | Front end admin login page | MUST HAVE | 3 | usama | 3- Completed
|  | 6 | Front end admin options page | MUST HAVE | 3 | usama | 3- Completed
|  | 7 | Front end real estate details page | MUST HAVE | 3 | usama | 3- Completed
|  | 8 | Front end purchase and payment page | MUST HAVE | 3 | smriti+usama | 3- Completed
|  | 9 | Front end chat bot page | MUST HAVE | 3 | smriti+usama | 3- Completed
|  | 2 | Back end user login validation | MUST HAVE | 3 | rounak | 3- Completed
|  |  | Back end user registration | MUST HAVE | 3 | rounak | 3- Completed
|  |  | Back end admin login validation | MUST HAVE | 3 | darshan | 3- Completed
|  |  | Back end admin crud operations | MUST HAVE | 3 | darshan | 3- Completed
|  |  | Back end purchase and payment integration | MUST HAVE | 3 | rounak+darshan | 3- Completed
|  | 3 | Handling program source code from git | MUST HAVE | 3 | kannappa | 3- Completed
|  |  | Building jenkins pipeline(autotriggering from git) | MUST HAVE | 3 | sagar | 3- Completed
|  |  | Connecting jenkins with nexus and building jar file | MUST HAVE | 3 | kannappa+sagar | 3- Completed
|  |  | Building docker image of project and pushing to docker hub | MUST HAVE | 3 | kannappa+sagar | 3- Completed
|  |  | Creation of server and worker node in ansible | MUST HAVE | 3 | kannappa+sagar | 3- Completed
|  |  | Working on kubernetes | MUST HAVE | 3 | kannappa+sagar | 3- Completed
|  |  | Mongodb table creation and insertion | MUST HAVE | 3 | kannappa+sagar | 3- Completed
|  |  | Swagger admin crud operations done | MUST HAVE | 3 | kannappa+sagar | 3- Completed
|  |  | Done with the download receipt option for user after purchasing a property | COULD HAVE | 3 | kannappa+sagar | 3- Completed
Note on F1: Kindly refrain from providing more than 8 points to user stories
Note on H1: Can be one from IN PROGRESS, COMPLETED, NOT STARTED

## SPRINT-1 BACKLOG
SPRINT 1 - BACKLOG
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Assiginee | Activity | Status | Original Estimate Effort (In Hours)
Original Estimate Effort (In Hours)
US 1 | T1 | Creating home page of our project | 2021-12-23 | 2021-12-25 | smriti | Coding | completed | 2
| T2 | Front end user login page | 2021-12-26 | 2021-12-26 | smriti | Coding | completed | 1
| T3 | Front end user contact and about page | 2021-12-27 | 2021-12-27 | smriti | Coding | completed | 1
| T4 | Front end admin login page | 2021-12-28 | 2021-12-28 | usama | Coding | completed | 1
| T5 | Front end admin options page and real estate details page | 2021-12-29 | 2021-12-30 | usama | Coding | completed | 2
| T6 | Front end chat bot page | 2021-12-31 | 2022-01-03 | smriti+usama | Coding | completed | 1
| T7 | Front end purchase and payment page | 2022-01-03 | 2022-01-04 | smriti+usama | Coding | completed | 2
US2 | T1 | Back end user login validation | 2021-12-23 | 2021-12-25 | rounak | Coding +integration+testing | completed | 5
| T2 | Back end user registration | 2021-12-26 | 2021-12-27 | rounak | Coding +integration+testing | completed | 6
| T3 | Back end admin login validation | 2021-12-28 | 2021-12-31 | darshan | Coding +integration+testing | completed | 4
| T4 | Back end admin crud operations | 2022-01-03 | 2022-01-07 | darshan | Coding +integration+testing | completed | 5
| T5 | Back end purchase and payment integration | 2022-01-11 | 2022-01-12 | rounak+darshan | Coding +integration+testing | completed | 4
| T9 | Done with the download receipt option for user after purchasing a property | 2022-01-12 | 2022-01-12 | rounak+darshan | Coding +integration+testing | completed | 4
| T10 | Added sold houses in admin portal | 2022-01-17 | 2022-01-19 | rounak+darshan | Coding +integration+testing | completed | 6
| T11 | Added purchase history in user portal | 2022-01-20 | 2022-01-20 | rounak+darshan | Coding +integration+testing | completed | 3
US3 | T1 | Handling program source code from git | 2021-12-23 | 2021-12-24 | kannappa | Build+testing | completed | 2
| T2 | Building jenkins pipeline(autotriggering from git) | 2021-12-25 | 2021-12-26 | sagar | Build+testing | completed | 3
| T3 | Connecting jenkins with nexus and building jar file | 2021-12-27 | 2021-12-30 | kannappa+sagar | Build+testing | completed | 4
| T4 | Building docker image of project and pushing to docker hub | 2021-12-31 | 2022-01-04 | kannappa+sagar | Build+testing | completed | 4
| T5 | Creation of server and worker node in ansible | 2022-01-05 | 2022-01-07 | kannappa+sagar | Build+testing | completed | 2
| T6 | Working on kubernetes | 2022-01-07 | 2022-01-07 | kannappa+sagar | Build+testing | completed | 3
| T7 | Mongodb table creation and insertion | 2022-01-10 | 2022-01-10 | kannappa+sagar | Build+testing | completed | 1
| T8 | Swagger admin crud operations done | 2022-01-11 | 2022-01-12 | kannappa+sagar | Build+testing | completed | 3
| T10 | Docker portmapping | 2022-01-17 | 2022-01-19 | kannappa+sagar | Build+testing | completed | 6
| T11 | Flowchart preparation of realestate and devops | 2022-01-21 | 2022-01-21 | kannappa+sagar | Build | completed | 1

## STAND UP MEETING
Sprint | US ID | Assigned On | Points Discussed | Impediments | Action Taken
1 | US01 | 2021-12-30 | Adding chat bot feature in front end NA | NA | NA
|  |  | Integration(Validation of user and admin) | It was not able to acces the css property | Resolved the issue using internal css
| US02 |  | Integration of jenkins with nexus on demo project | faced issue while connecting jenkins with nexus | Resolved by giving the correct path of jar file
Resolved that issue by removing the errors
|  | 2021-12-31 | Admin options integrated and payment page added for user in frontend | NA | NA
|  |  | Integration of crud operation for dummy table in backend | After adding the content it was not getting saved in the database | Did some changes in the column name of the database table and matched it with the one that was present in the entity class in backend
|  |  | Docker implementation on demo project | Faced multiple issues for 3 days like target java 11 was invalid,mvn command not found | Resolved first issue using docker base image.
US03
|  | 2022-01-03 | Enhanced our page by changing some properties in css file | NA | NA
|  |  | Integration of crud operation for real admin options in backend | Css property was not getting accessed | Internal css was added to resolve this
|  |  | Creating war file for real estate project in nexus | Jenkins file and pom file not found error was encountered | Resolved issue by giving the full path of the git repository and also we made some changes with the jenkins file.
1 | US 04
|  | 2022-01-04 | Enhanced our page by changing some properties in css file | NA | NA
|  |  | Was working on search option for admin and user both | We were not able to search the property of house by giving pid | Currently working on that
| US 05 |  | Creating docker images and containers for the real project | We are not able to perform port mapping after the creation of docker images | Currently working on that
|  | 2022-01-05 | Enhanced our page by changing some properties in css file | NA | NA
| US 06 |  | Integration of crud operation of admin options | some of the updated attributes were not getting saved in the database | Resolved by setting same name for entity and table column
|  |  | Woking on port mapping for container | We are not able to access the container ip on browser | Currently working on that
1 | US 03 | 2022-01-06 | Enhanced our page by changing some properties in css file
|  |  | Working on search operation of admin options | After refreshing the page admin name is not showing | Currently working on that
|  |  | Creation of server and worker node in ansible | NA | NA
US 04
| US05 | 2022-01-07 | Search option for both admin and user completed successfully | NA | NA
|  |  | connecting master and worker node and creating pods in kubernetes | NA | NA
US06
|  | 2022-01-10 | Mongodb table creation and insertion | NA | NA
| US07 |  | Swagger admin crud operations done | NA | 2 api’s have been created and 2 more are yet to be done in admin part
|  |  | done with ppt creation on devops | NA | NA
|  |  | Backend userportal and adminportal username issue | The username in user portal and admin portal was not reflecting after navigating to another page | Working on this issue
|  | 2022-01-11 | Backend userportal and adminportal username issue | The username in user portal and admin portal was not reflecting after navigating to another page | Using the concept of global variable
|  |  | Payment and purchase integration in backend for user | After clicking on purchase button ,it was not able to save the purchased detail in database | working on it currently
| US08 |  | Swagger admin crud operations done | NA | NA
|  | 2022-01-12 | Payment and purchase integration in backend for user | After clicking on purchase button ,it was not able to save the purchased detail in database | Mapped the same name of table in the pojo class of project
|  |  | Done with the download receipt option for user after purchasing a property | NA | NA
1 | US09 |  | working on swagger user side operations
|  | 2022-01-17 | Added sold houses in admin portal | NA | NA
| US10 |  | Docker portmapping | NA | NA
|  | 2022-01-18 | Added sold houses in admin portal | NA | NA
|  |  | Docker portmapping | NA | NA
US02
|  | 2022-01-19 | Enhancement in adminportal | NA | NA
|  | 2022-01-20 | Added purchase history in user portal | NA | NA
US07
| US08 | 2022-01-21 | Flowchart preparation of realestate and devops | NA | NA
US09
US10